**City of Knoxville Housing and Neighborhood Development**

**PY2021-2022 Annual Action Plan Timeline**

Key:

Public Input Process

Funding Process

Consultation with Community Partners August 2020 – March 2021

Public Meeting #1 (via Zoom) January 14, 2021

Feedback on priorities and changing conditions

Staff develop draft Plan February – May 2021

Incorporates priorities in application documents

CDBG and Homeless Grants Applications Released February 1

[www.knoxvilletn.gov/development](http://www.knoxvilletn.gov/development),

under “Current Grant Opportunities”

Technical Assistance Workshops (via Zoom) February 4\* & February 9\*

*\*Attendance at one is mandatory for applicants* (6-8 PM) (1-3 PM)

CDBG and Homeless Grants Applications Due February 19, 2021 (noon)

Staff review applications, compare with resources February 19 – March

available, and present recommendations to Administration

Staff incorporates proposed projects, activities and March – April 1

resources into draft Plan

Draft Plan Made Available for Public Review April 2

30-day Public Comment Period April 2 - May 3

Public Meeting #2 (via Zoom) April 27, 6:00 PM

City Council Workshop (via Zoom) April 29, 6:00 PM

City Council Meeting - Review / Approval (via Zoom) May 4, 6:00 PM

Due to HUD May 14, 2021

For more information or to provide comment, please contact: Linda Rust, CD Administrator

lrust@knoxvilletn.gov or

Housing and Neighborhood Development, P.O. Box 1631, Knoxville, TN 37901